Escuela Internacional Sampedrana

San Pedro Sula, Cortés, Honduras

Escuela Internacional La Lima

La Lima, Cortés, Honduras

MANO A MANO III

MENTORING ACTION PLAN

Vision

All of the Early Childhood Staff (teachers and administrators) will be fully immersed in the implementation of the “9 Educational Components” and Developmentally Appropriate Practices”.

Goal

Begin the process of evaluating our ECC program structure and academic environments in order to ensure that our students are taught under a quality and developmentally appropriate setting.

Objectives

- Provide teachers with the Instructional and assessment information and tools, needed to offer developmentally appropriate practices.

- Create a sense of empowerment and awareness on developmentally appropriate practices.

Activities

- Provide all Early Childhood teachers with ECERS/SACERS and CLASS manuals.

- Guide all EC teachers in the proper implementation of the ECERS/SACERS and CLASS assessment tools, both in EIS and EILL campuses.

- Guide teachers in the creation of their own “Teacher’s Notebook”

Timeline

- By October 2010, all Early Childhood teachers will have their own ECERS/SACERS and CLASS Manuals inside their classroom.

- IMPLEMENTATION OF ECERS/SACERS AND CLASS ASSESSMENT TOOLS

Every month all EC teachers will be presented with one section of the ECERS/SACERS and two sections of the CLASS manuals, and will be asked to assess themselves with the guidance of the Mano a Mano Mentors. Two weeks later, the mentors will do individual meetings to discuss results and develop an “Action Plan”.

The school has already scheduled Professional Development Sessions, throughout the school year, from which 15-30 min. will be taken to present to teachers the sections assigned to the month. These sessions will be held in the conference room of each division.

OCTOBER 2010:  Space and Furnishing & Positive and Negative Climate

Professional Development Session held on: Oct. 5th, 2010

Individual Session to discuss outcome: Week of Oct. 25-29, 2010

NOVEMBER 2010:  Personal Care Routines/Health and Safety & Teacher Sensitivity and Regard for Students Perspectives

Professional Development Session held on:  Nov 16, 2010

Individual Session to discuss outcome: Week of Nov. 22-26, 2010

DECEMBER 2010: Language reasoning (for grades Nursery to Kinder)

The presentation of the ECERS section will be done by the mentor during each grade’s Team Meeting.

Individual Session to discuss outcome: Week of Dec. 13-16, 2010

JANUARY 2011: Activities & In-Class Behavior Management and Productivity

Professional Development Session held on: Jan 3rd, 2010

Individual Session to discuss outcome: Week of Jan. 24-28, 2011

FEBRUARY 2011: Interactions & Instructional Learning Formats and Concept Development

Professional Development Session held on: Jan 25th, 2010

Individual Session to discuss outcome: Week of Feb. 21-25, 2011

MARCH 2011: Program Structure & Quality of Feedback and Language Modeling

Professional Development Session held on: Feb 22nd, 2011

Individual Session to discuss outcome: Week of Jan. 21-25, 2011

APRIL 2011: Provisions to Parents/ Staff Development

Professional Development Session held on:

Individual Session to discuss outcome: Week of Jan. 24-28, 2011

- Administrators will be in charge of assessing the Parents and Staff area

- Student Support Services Team will be in charge of assessing Special Needs Supplementary Items area.

3. CREATION OF “TEACHER’S NOTEBOOK”

The TEACHER’S NOTEOOK is a great tool for teachers were they will be able to keep a record of all the assessment methods being used and student profile and progress throughout the year.

The Mano a Mano mentor’s have already been creating the model for the Teacher’s Notebook and will present to all Early Childhood teachers.

Team Leaders will present the model of the Teacher’s Notebook in the week of Sept 27 through Oct 1st, 2010.

Every two Friday’s, teachers will meet to review, discuss, and update Teacher’s Notebook”.

Needed Support

Administrative Support: Administrators will have to assign the Mano a Mano team 15-30 min. of each Professional Development Session to present each of the Areas of the ECERS/SACERS and CLASS manuals.

Budgetary Support: School administrators will purchase:

- Original copies of the ECERS/SACERS and CLASS manuals for each early childhood teacher.

- 1.5 inch binders for each homeroom teacher.