PLAN FOR CHANGE AND MENTORING

Pily Fernandez and Flor Artigas

Vision:

Change teacher´s old way of thinking towards Developmentally Appropriated Practices.

- GOAL FOR CHANGE: AND MENTORING:

Mentor the Early childhood teachers towards DAP.

- CHANGE AND MENTORING OBJECTIVES:

- Structure the classroom that is DAP.

- To help them learn the best way of “how to solve conflicts” according to a research.

- Show them new technique to implement Active Listening in their classrooms.

- SPECIFIC ACTIVITIES FOR MEETING EACH OBJECTIVE:

- Structure the classroom to a DAP.

Present to all the early childhood staff our project.   To introduce the ECER-S book so that they can use it to arrange their classroom in a developmentally appropriated way.

- Solve conflicts in a positive way.

In a meeting, we will show our co-workers some videos about how to solve conflicts in a positive way according to research.

- Active Listening.

Explain teachers new technique to implement active listening in their classrooms, so that students feel cared about and emotionally connected to their school.

- TIMELINE WITH ACTION STEPS IDENTIFIED:

| Objectives | Activities | Timeline |
| --- | --- | --- |
| Structure the classroom to a DAP. | - Present to all the Early childhood staff our project. - Interchange different points of view on what they think of the DAP classroom environment. - To introduce the ECER-S book so that they can use it to arrange their classroom in a developmentally appropriated way. | August–September during Early childhood staff meetings. |
| To help them learn the best way of “how to solve conflicts” according to a research. | - In a meeting, we will show our co-workers some videos about how to solve conflicts in a positive way: - High-scoop video - Power point presentation (Mano a Mano) - Discuss different points of view in how to implement these in their classrooms. | In-service 1st meeting (September 24th,2010). In-service 2nd meeting (October 26th, 2010). |
| Show them new technique to implement Active Listening in their classrooms. | - Present Positive Discipline Research by Dr. Jane Nelsen using resources on website. - Discuss different points of view in how to implement these in their classrooms. - Revision based on survey and research comments/feedback | In-service 3rd meeting (January 4th, 2010). |

- All of these activities will be presented in the in-service meeting in the Multipurpose Conference Room.  These meetings are mandatory for all the early childhood staff.

- ANY SUPPOERT YOU WILL NEED: (ADMISTRATIVE, BUDGETARY, STAFF, PARENT INVOLVEMENT, ETC.)

- We will need the support of the early childhood Principal, copies of the ECERS, video equipment, and money to buy some equipment to start working on Developmentally Appropriated classrooms.