MANO A MANO III

Plan for Change and Mentoring

PAN-AMERICAN SCHOOL

COSTA RICA

September, 2010

This plan involves the mentoring of a group of early childhood teachers by their coordinator for the remainder of 2010 and during 2011. However, it includes aspects that hopefully will promote the independence, knowledge and skills of individuals to eventually become mentors of developmentally appropriate practices to others.

- GOAL

In Pan-American School continue to implement in Early Childhood, strategies that will result in the application and improvement of developmentally appropriate practices.

- OBJECTIVES

- Continue the implementation of the ECERS-R by ECE teachers as a tool of self-evaluation, therefore having a direct effect on early childhood environments.

- Use CLASS PRE-K as a resource for self-analysis to improve developmentally appropriate practices in early childhood classrooms.

- Implement strategies for professional development among early childhood staff that will increase and improve the application of developmentally appropriate practices.

- ACTIVITIES

- Use of ECERS-R

| Activity | When | Where | Timeline | Who | Resources | Support needed |
| --- | --- | --- | --- | --- | --- | --- |
| All ECE teachers will continue to self-evaluate their own classrooms using the ECERS-R. | Monthly | In early childhood classrooms. | - II Semester 2010 - I & II Semester 2011 | ECE teachers | Copies of ECERS-R for each ECE section | ECE Coordinator’s supervision and guidance. |
| ECE Lead Teachers will create an Action Plan to improve classroom environments based on their results of the ECERS-R. | Monthly | In early childhood classrooms. | -II Semester 2010 - I & II Semester 2011 | ECE teachers | -ECERS-R -Action Plan template | ECE Coordinator’s supervision and guidance. |
| ECE Lead Teachers in each level will meet with the ECE Coordinator to go over the ECERS-R results, the ongoing Action Plans and general progress. | Once a month | In early childhood classrooms. | -II Semester 2010 - I & II Semester 2011 | ECE teachers & ECE Coordinator | -ECERS-R -ECE teachers individual ECERS-R Action Plan | -ECE Coordinator -Financial support |
| ECE Coordinator will observe individual ECE classrooms and provide individual feedback based on observations and using the ECE teacher’s Action Plan, ECERS-R, and a class observation checklist as guides. | Once a month | Early childhood classrooms | II Semester 2010 - I & II Semester 2011 | ECE Coordinator | -ECE teacher’s Action Plan -ECERS-R -Class Observation checklist | ECE teachers |

- Use of CLASS PRE-K

| Activity | Frequency | Where | Timeline | Who | Resources | Support needed |
| --- | --- | --- | --- | --- | --- | --- |
| As a group, ECE teachers will analyze and discuss each section of the CLASS PRE-K. (Two sections will be done a month.) Teachers will be encouraged to make critiques of real and hypothetical problems (when appropriate) and come up with possible solutions based on the CLASS PRE-K. | Once a month for approximately 30 minutes. | In early childhood level meetings. | -I Semester 2011 (Feb.-June) | ECE teachers & ECE Coordinator | Copies of the CLASS PRE-K for each ECE class | -ECE Coordinator’s supervision and guidance. -Financial support to acquire copies of the CLASS |
| Each ECE Lead Teacher will organize throughout the year, video-taping of herself doing different activities with the children in her class. The video-taping will be done by another person. The recommended duration of each video tape is approximately between 15-30 minutes. The goal is to do at least two video tapes in 2011. | Once every three months | In early childhood classrooms. | -April-June 2011 -II Semester 2011 | ECE Lead Teachers | -Video camera, tripod -Another person to video tape | -ECE Coordinator’s guidance -School Administration |
| Each ECE Lead Teacher will analyze with the ECE Coordinator the video tapes of her class. The CLASS PRE-K will be used as a guide for improvement. | Once every three months | ECE Coordinator’s office | -May-June 2011 -II Semester 2011 | -ECE Lead Teachers -ECE Coordinator | Individual videos of each ECE classroom | ECE Coordinator’s guidance |
| Each ECE Lead Teacher will create an Action Plan for improvement of classroom interactions based on the results of their video tape analysis. | Once every three months | In early childhood classrooms. | -May-June 2011 -II Semester 2011 | ECE teachers | -CLASS PRE-K -Action Plan template (which will be created) | ECE Coordinator’s supervision and guidance. |
| ECE Coordinator will observe ECE classrooms and provide feedback based on the goals set out in the teacher’s Action Plan which in turn is aligned to the CLASS PRE-K. | Monthly | In early childhood classrooms. | -May-June 2011 -II Semester 2011 | -ECE Coordinator -ECE teachers | -CLASS PRE-K -Individual Action Plan done by each ECE Lead Teacher | -ECE Lead Teacher -ECE Coordinator |

- Professional Development Strategies

| Activity | Frequency | Where | Timeline | Who | Resources | Support needed |
| --- | --- | --- | --- | --- | --- | --- |
| ECE teachers are encouraged to present professional development sessions based on developmentally appropriate practices for the ECE team. This activity is not mandatory. | One different person present one session every two months (30-50 minutes) | ECE Level Meetings | -Sept.- Nov. 2010 -I & II Semester 2011 | ECE Teachers | Various - depending on the topic of the session | ECE Coordinator |
| ECE Coordinator prepares a session on developmentally appropriate practices for the ECE team. | One session every month (30-50 minutes) | ECE Level Meetings | -Sept.- Nov. 2010 -I & II Semester 2011 | ECE Coordinator | NAEYC resources –DVDs, Young Children, etc. | ECE teachers |
| ECE teachers form an after school professional development “club” to discuss topics of interest related to DAP. Participants are encouraged to share their findings with the ECE team in ECE meetings. These two activities are not mandatory. | After school | On campus | I & II Semester 2011 | ECE teachers | DAP resources | ECE teachers & ECE Coordinator |
| ECE teachers analyze articles and short videos on DAP in ECE meetings brought by ECE Coordinator and/or other ECE teachers. | Once a month (10-15 minutes) | ECE Level Meetings | -Sept.- Nov. 2010 -I & II Semester 2011 | ECE Coordinator | Articles & videos on DAP, video beam, laptop | ECE teachers |
| ECE teachers observe other ECE classes and reflect on the experience with the goal of improving their own work. A peer observation class checklist will be used. | Once every two months (30 minutes) | ECE classrooms | I & II Semester 2011 | ECE teachers | -ECE classrooms -ECERS-R -CLASS PRE-K -NAEYC DAP 3rd Ed. (book) - Peer class observation checklist | ECE Coordinator’s supervision & guidance |
| ECE teachers investigate and prepare an innovation on an area of DAP that they have developed in their classroom throughout the school year. | Once a year | -ECE classrooms -ECE Level Meetings | Innovation 2010 2011 school years Presentation --Oct.-Nov 2010 -Oct.-Nov. 2011 | ECE teachers | -Various DAP resources -ECE classrooms -Audio visuals | ECE Coordinator |
| A group of ECE teachers go to the 2011 NAEYC Conference in Orlando, FL. | Once | Orlando, FL. | Nov. 2011 | Some ECE teachers & Coordinator | -Finances -Time & permission to go | School Administration |

Updated: Sept. 5, 2010