CHANGE AND MENTORING PLAN

MANO A MANO III

Santo Domingo, Dominican Republic

September, 2010

Carmen Rocío Castillo

Francia Gómez

Esther Morales

VISION

Build up a preschool wide awareness of the importance of promoting the development of priming skills needed for reading and writing

GOAL FOR CHANGE AND MENTORING:

Involve preschool teachers in the implementation of developmentally appropriate practices that help develop priming skills in preschool students needed for reading and writing.

CHANGE AND MENTORING OBJECTIVES:

- Make preschool teachers conscious about the importance of implementing DAP, Developmentally Appropriate Practices, in planning and instruction that will help develop student’ priming skills needed for reading and writing.

- Train teachers in the use of the ECER-S to self-assess the areas of Language reasoning and Activities.

- Implement activities and strategies in preschool classrooms that help develop student’ priming skills.

- Set preschool classrooms with areas and resources with that help develop student’ priming skills.

- Monitor the implementation of activities and strategies in planning and instruction, as well as the use of resources in preschool classrooms that help develop student’ priming skills.

- Assess students’ reading and writing skills throughout the school year and take actions to help them improve in these areas according to individual needs.

SPECIFIC ACTIVITIES FOR MEETING EACH OBJECTIVE:

- a) Research about Developmentally Appropriate Practices and Multiple Intelligences in preschool.

b) Prepare workshops for teachers about DAP and Multiple Intelligences connected to contents previously worked on about Priming Skills.

c) Present workshop to preschool teachers.

2. a) Present workshop to teachers about the use of the ECER-S in the areas of: Language reasoning and Activities.

b)Engage teachers in self evaluation sessions using the language reasoning and activities areas of the ECER-S.

- a) Engage teachers in the planning and implementation of activities and strategies in preschool classrooms that help develop student’ priming skills, including more outdoor activities, brain break sessions, experiments, cooking activities, etc.

b) Reduce the use of worksheets and integrate more hands-on activities and the creation of tridimensional materials made by students spontaneously.

- a) Acquire and integrate resources in preschool classrooms that help develop priming skills, such as sandbox, water box, plants,/ for students to grow and care, pets that will be taken home regularly by each student, , musical instruments, puppets, surprise boxes, resources to explore textures, resources to explore smells, etc.

b) Integrate a quiet area in preschool classrooms for the students to have time to be apart and rest when needed.

c) Display materials and students work at students’ eye level for them to revisit their work.

d) Exhibit pictures of students working at the classroom in varied activities with documentation of the purpose and description of the activity.

e) Exhibit signs of steps children need to follow to complete assignments.

- a) Create a Plan Rubric to assess teachers’ plans and monitor the correct and balanced integration of developmentally appropriate practices that respect multiple intelligences in students, and help them develop priming skills.

b) Present Plan Rubric to teachers on a regular basis for them to make adjustments needed in planning and instruction that help students further develop priming skills and multiple intelligences.

- a) Create reading and writing rubrics for preschool students

b) Apply reading and writing rubrics to assess students’ performance in these areas on a regular basis.

c) Analyze and compare students’ assessment results throughout the school year.

d) Plan actions to be implemented in the classroom to help students continue developing and improving priming skills as well as reading and writing skills

TIMELINE WITH ACTION STEPS IDENTIFIED

| OBJECTIVE | ACTIVITIES | ACTION STEPS | TIME | RESOURCES NEEDED | PEOPLE RESPONSIBLE |
| --- | --- | --- | --- | --- | --- |
| 1. Make preschool teachers conscious about the importance of implementing DAP, Developmentally Appropriate Practices, in planning and instruction that will help develop student’ priming skills needed for reading and writing. | 1.a) Research about Developmentally Appropriate Practices and Multiple Intelligences in preschool. | -Investigate in Internet, books and materials brought from Antigua contents regarding Developmentally Appropriate Practices and Multiple Intelligences -Add contents connected to our previous experiences in the classroom. -Link contents to real practices in our school | July-August, 2010 | -Internet -Books -Library -Mano a Mano resources | -Esther morales -Francia Gómez -Rocío Castillo |
|  | 1.b) Prepare workshops for teachers about DAP and Multiple Intelligences connected to contents previously worked on about Priming Skills. | -Meet to prepare power point presentation and materials for the workshop. -Set time and place in the school to present workshop | July-August, 2010 |  | -Esther Morales -Francia Gómez -Rocío Castillo |
|  | 1.c) Present workshop to preschool teachers | -Teachers met in a classroom to receive the workshop -Teachers from the neighbor school “Mi Colegio” were invited to join the MCSchool group of teachers. *Dynamics were integrated such as the Multiple Intelligence test, small groups that worked in identifying relevant type of intelligence, creation of activities list that promote priming skills, etc. | August 3rd, 2010 |  | -Esther Morales -Francia Gómez -Rocío Castillo |
| 2.Train teachers in the use of the ECER-S to self-assess the areas of Language reasoning and Activities | 2.a) Present workshop to teachers about the use of the ECER-S in the areas of: Language reasoning and Activities. | -Read again the ECERS document -Meet to prepare power point presentation and materials (hand outs) for the workshop. -Set time and place in the school to present workshop -Link contents to practices in our school. | October 2010 | ECERS Document Data Show Power point presentation | -Esther Morales -Francia Gómez -Rocío Castillo |
|  | 2.b)Engage teachers in self evaluation sessions using the language reasoning and activities areas of the ECER-S. | -As a preschool coordinator (Rocío Castillo) and as the Preschool Psychology (Esther Morales) we are going to motivate teachers to use the ECERS (in the areas of Language reasoning and Activities) as a guide to improve their practice. | November 2010 | ECERS Document Teachers Observation Form | -Rocío Castillo -Esther Morales |
| 3. Implement activities and strategies in preschool classrooms that help develop student’ priming skills. | 3.a)Engage teachers in the planning and Implementation of activities and strategies in preschool classrooms that help develop student’ priming skills, including more outdoor activities, brain break sessions, experiments, cooking activities, etc. | -Meet with teachers to motivate them implement these strategies and change some practices -Kinder A classroom (Ms. Francia’s classroom) will be used as a model room for other teachers to observe and get ideas to be implemented | Ongoing 2010 | Observations Check Plans Meetings | -Rocío Castillo -Esther Morales |
|  | 3.b) Reduce the use of worksheets and integrate more hands-on activities and the creation of tridimensional materials made by students spontaneously. | -Teachers will be required to plan and implement this kind of activities -Kinder A classroom (Ms. Francia’s classroom) will be used as a model room for other teachers to observe and get ideas to be implemented | Ongoing 2010 | Observations Check Plans Meetings | -Rocío Castillo -Esther Morales -Francia Gómez |
| 4. Set preschool classrooms with areas and resources with that help develop student’ priming skills. | 4.a) Acquire and integrate resources in preschool classrooms that help develop priming skills, such as sandbox, water box, plants,/ for students to grow and care, pets that will be taken home regularly by each student, , musical instruments, puppets, surprise boxes, resources to explore textures, resources to explore smells, etc. | -Present new ideas to School Directors School Budget Buy resources needed Involve parents in the acquisition of resources (plants, pets, pots, etc) -Set areas of the school where plants, pets and sandboxes will be placed -Start including activities with these resources in planning and instruction | September-November 2010 | Plants Pets Pots Lesson plan evaluation form Calss observation Pictures | School Directors Rocio Castillo Esther Morales Francia Gomez |
|  | 4.b) Integrate a quiet area in preschool classrooms for the students to have time to be apart and rest when needed. | -Motivate teachers to get involved in this project and to see the importance of a private space. -Observe classrooms | Next School Year | Little Tents Little Carpets Pillows Cozy toys Class observation forms | Directors Rocío Castillo Esther Morales Francia Gomez |
|  | 4.c) Display materials and students work at students’ eye level for them to revisit their work. | -Motivate teachers to display everything on child’s eye level -Observe classrooms | August 2010 | Bulletin Boards Strings Walls Shelves Class observation forms | Rocio Castillo Esther Morales Francia Gomez |
|  | 4.d) Exhibit pictures of students working at the classroom in varied activities with documentation of the purpose and description of the activity. | Motivate teachers Take pictures of activities Document activities | Next School year | Camera Computer Printer | Rocio Castillo Esther Morales |
|  | 4.e) Exhibit signs of steps children need to follow to complete assignments. | Place flashcards in the classroom that show children steps to accomplish a task. | Next School Year | Flashcards Pictures | Rocio Castillo Esther Morales |
| 5. Monitor the implementation of activities and strategies in planning and instruction, as well as the use of resources in preschool classrooms that help develop student’ priming skills. | 5.a) Create a Plan Rubric to assess teachers’ plans and monitor the correct and balanced integration of developmentally appropriate practices that respect multiple intelligences in students, and help them develop priming skills. | -Check the ECERS Documents to create our own rubric. Share the draft to all staff members. -Check plans. | September 2010-June 2011 |  | Rocio Castillo |
|  | 5.b) Present Plan Rubric to teachers on a regular basis for them to make adjustments needed in planning and instruction that help students further develop priming skills and multiple intelligences. | -Meet with teachers -Set a place and time | September 2010-June 2011 |  | Rocio Castillo |
| 6. Assess students’ reading and writing skills throughout the school year and take actions to help them improve in these areas according to individual needs. | 6.a) Create reading and writing rubrics for preschool students | Check our Curriculum Check kinder rubrics To make the pertinent changes and connect them to create Nursery and Pre K ones. | October 2010-June 2011 | Curriculum Plans Old rubrics | Rocio Castillo Nursery, Prekinder and Kinder Teachers. |
|  | 6.b) Apply reading and writing rubrics to assess students’ performance in these areas on a regular basis. | Establish a moment to apply and asses these rubrics. | October 2010-June 2011 | Time to set up meetings. | Rocio Castillo Nursery, Prekinder and Kinder Teachers. |
|  | 6.c) Analyze and compare students’ assessment results throughout the school year. | File the results of each grade. Analyze the results. Share with other teachers. | October 2010-June 2011 | Time to set up meetings. | Rocio Castillo Nursery, Prekinder and Kinder Teachers. |
|  | 6.d) Plan actions to be implemented in the classroom to help students continue developing and improving priming skills as well as reading and writing skills | Keep teachers motivated to develop and improve Priming Skills Follow up | October 2010-June 2011 | Time to share experiences. Research | Rocio Castillo Nursery, Prekinder and Kinder Teachers. |

SUPPORT NEEDED: (ADMISTRATIVE, BUDGETARY, STAFF, PARENT INVOLVEMENT, ETC.)

- We had a meeting with the Administrative School Director and the Academic School Director on Tuesday, august 31st, to present the Action Steps of our project and explain the support required from the school. The school Directors approved the plan and gave suggestions about ways we could involve parents in the process.

- The School will facilitate the resources needed to print pictures on a bi-weekly basis, to present documentation of student’s work in the hallways. The school will also provide resources needed throughout the school year to implement activities planned that need this support.

- Parents will be invited to participate in varied activities throughout the school year: they will be “teachers for one day” and will have the opportunity to conduct many of the activities planned that promote the development of priming skills.

- Parents will also be invited to participate in the acquisition of plants and pets for each preschool classroom.

- Teachers will have the opportunity to share experiences in “Shared experience sessions” and grade team meetings that will take place throughout the school year.